## Feuil1
MSN | DS | Realsed | Modification | VB | Indice | CAT. | Statut Windshill | CA code | DR | Status | Début Planifiée | Designer | Start Date | End Date | Due Date Design | Progress Design | Checker | Start Date | End Date | Due Date Check | Progress Check | DR | Status | Début Planifiée | MUR Qualité Plan 2D | Start Date | End Date | Due Date Design | Progress Design | Impression | Date impression
11348 | E92911089000 | C00 | Création | 4001VB | 002-C | XXL | Completed | DB807 | DR-0000027266 | FINISHED V | 2023-03-14 | R.ABBASSI | 2023-03-14 | 2023-03-27 | 2023-03-27 | On Time | K.GHLIMI | 2023-04-04 | 2023-04-11 | 2023-04-11 | On Time
11348 | E92911089000 | C00 | PL0180416 | 4001VB | 002-C1 | XXL | Completed | DB807 | DR-0000017186 | FINISHED V | 2023-03-14 | R.ABBASSI | 2023-03-14 | 2023-03-27 | 2023-03-27 | On Time | K.GHLIMI | 2023-04-04 | 2023-04-11 | 2023-04-11 | On Time
11348 | E92911089000 | C00 | RDR0181352 | 4001VB | 002-C2 | XXL | Completed | DB807 | DR-0000017263/DR-0000017266 | FINISHED V | 2023-03-14 | R.ABBASSI | 2023-03-14 | 2023-03-27 | 2023-03-27 | On Time | K.GHLIMI | 2023-04-04 | 2023-04-11 | 2023-04-11 | On Time
11348 | E92911089000 | C00 | RDR0181390 | 4001VB | 002-C3 | XXL | Completed | DB807 | DR-0000017265/DR-0000027408 | FINISHED V | 2023-03-14 | R.ABBASSI | 2023-03-14 | 2023-03-27 | 2023-03-27 | On Time | K.GHLIMI | 2023-04-04 | 2023-04-11 | 2023-04-11 | On Time
11348 | E92911089000 | C00 | RDR0181425 | 4001VB | 002-C4 | XXL | Completed | DB807 | DR-0000027294/DR-0000027295 | FINISHED V | 2023-03-14 | R.ABBASSI | 2023-03-14 | 2023-03-27 | 2023-03-27 | On Time | K.GHLIMI | 2023-04-04 | 2023-04-11 | 2023-04-11 | On Time
11348 | E92911089000 | C00 | RDR0181736 | 4001VB | 002-C5 | XXL | Completed | DB807 | DR-0000027329 | FINISHED V | 2023-03-14 | R.ABBASSI | 2023-03-14 | 2023-03-27 | 2023-03-27 | On Time | K.GHLIMI | 2023-04-04 | 2023-04-11 | 2023-04-11 | On Time
11348 | E92911089000 | C00 | RDR0181729 | 4001VB | 002-C6 | XXL | Completed | DB807 | DR-0000027337 | FINISHED V | 2023-03-14 | R.ABBASSI | 2023-03-14 | 2023-03-27 | 2023-03-27 | On Time | K.GHLIMI | 2023-04-04 | 2023-04-11 | 2023-04-11 | On Time
11348 | E92911089000 | C00 | RDR0181445 | 4001VB | 002-C7 | XXL | Completed | DB807 | DR-0000027338 | FINISHED V | 2023-03-14 | R.ABBASSI | 2023-03-14 | 2023-03-27 | 2023-03-27 | On Time | K.GHLIMI | 2023-04-04 | 2023-04-11 | 2023-04-11 | On Time
11348 | E92911089000 | C00 | RDR0181806 | 4001VB | 002-C8 | XXL | Completed | DB807 | DR-0000027339 | FINISHED V | 2023-03-14 | R.ABBASSI | 2023-03-14 | 2023-03-27 | 2023-03-27 | On Time | K.GHLIMI | 2023-04-04 | 2023-04-11 | 2023-04-11 | On Time
11348 | E92911089000 | C00 | E92911089_C00_biss | 4001VB | 002-C9 | XXL | Completed | DB807 | DR-0000027419 | FINISHED V | 2023-03-14 | R.ABBASSI | 2023-03-14 | 2023-03-27 | 2023-03-27 | On Time | K.GHLIMI | 2023-04-04 | 2023-04-11 | 2023-04-11 | On Time
11348 | E92911089000 | C00 | E92911089000EJ | 4001VB | 002-C10 | XXL | Completed | DB807 | DR-0000027449 | FINISHED V | 2023-03-14 | R.ABBASSI | 2023-03-14 | 2023-03-27 | 2023-03-27 | On Time | K.GHLIMI | 2023-04-04 | 2023-04-11 | 2023-04-11 | On Time
11348 | E92911089000 | C00 | RDR0182287 | 4001VB | 002-C11 | XXL | Completed | DB807 | DR-0000027496 | FINISHED V | 2023-04-25 | R.ABBASSI | 2023-04-25 | 2023-04-26 | 2023-04-26 | On Time | K.GHLIMI | 2023-04-26 | 2023-04-27 | 2023-04-27 | On Time
11348 | E92911089000 | C00 | EVO23-030 | 4001VB | 002-C11-1 | XXL | N/A | DB807 | N/A | FINISHED V | 2023-04-25 | R.ABBASSI | 2023-04-25 | 2023-04-26 | 2023-04-26 | On Time | K.GHLIMI | 2023-04-26 | 2023-04-27 | 2023-04-27 | On Time
11348 | E92911089000 | C00 | PL0181991/EVO23-036 | 4001VB | 002-C12-1 | XXL | Completed | DB807 | DR-0000027441 | FINISHED V | 2023-05-05 | R.ABBASSI | 2023-05-05 | 2023-05-05 | 2023-05-05 | On Time | K.GHLIMI | 2023-05-05 | 2023-05-05 | 2023-05-05 | On Time
11348 | E92911089000 | C00 | Création | 2010VB | A | XXL | N/A | DB807 | DR-0000027266 | FINISHED V | 2023-05-05 | R.ABBASSI | 2023-05-03 | 2023-05-04 | 2023-05-05 | On Time | M.AYNAOU | 2023-05-05 | 2023-05-05 | 2023-05-05 | On Time
11348 | E92911089000 | C00 | EVO23-043 | 2010VB | A-1 | XXL | N/A | DB807 | N/A | FINISHED V | 2023-05-05 | R.ABBASSI | 2023-05-07 | 2023-05-08 | 2023-05-08 | On Time | M.AYNAOU | 2023-05-09 | 2023-05-09 | 2023-05-10 | On Time
11348 | E92911089000 | C00 | RDR0182877 | 4001VB | 002-C13 | XXL | Completed | DB807 | DR-0000027651 | FINISHED V | 2023-06-07 | R.ABBASSI | 2023-06-07 | 2023-06-07 | 2023-06-07 | On Time | K.GHLIMI | 2023-06-07 | 2023-06-07 | 2023-06-08 | On Time
11348 | E92911089000 | C00 | EVO 023-063 | 4001VB | 002-C13-1 | XXL | N/A | DB807 | N/A | FINISHED V | 2023-07-06 | R.ABBASSI | 2023-07-06 | 2023-07-06 | 2023-07-06 | On Time | K.GHLIMI | 2023-07-06 | 2023-07-06 | 2023-07-06 | On Time
11348 | E92911089000 | C00 | PL0182624 | 4001VB | 002-C13-1 | XXL | Completed | DB807 | DR-0000027646 | FINISHED V | 2023-07-06 | PAS d'impact | PAS d'impact | PAS d'impact | PAS d'impact | On Time | PAS d'impact | PAS d'impact | PAS d'impact | PAS d'impact | On Time
11348 | E92911089000 | C00 | C20D875A | 4001VB | 002-C14 | XXL | Hind | DB807 | DR-0000027696 | FINISHED V | 2023-07-06 | R.ABBASSI | 2023-07-06 | 2023-07-06 | 2023-07-06 | On Time | K.GHLIMI | 2023-07-06 | 2023-07-06 | 2023-07-06 | On Time
11504 | E92911181000 | A00 | Création | 2010VB | 008-A8 | XXXL |  | DB807 | DR-0000028039 | FINISHED V | 2023-09-15 | R.ABBASSI | 2023-10-15 | 2023-10-19 | 2023-10-19 | On Time | F.OUZZA | 2023-10-26 | 2023-10-28 | 2023-10-27 | Late
11504 | E92911181000 | A00 | RDR0182877 | 2010VB | 008-A11-2 | XXXL |  | DB807 |  | FINISHED V | 2023-09-15 | R.ABBASSI | 2023-10-15 | 2023-10-19 | 2023-10-19 | On Time | F.OUZZA | 2023-10-26 | 2023-10-28 | 2023-10-27 | Late
11504 | E92911181000 | A00 | PL0181991 | 2010VB | 008-A11-2 | XXXL |  | DB807 | DR-0000027979 | FINISHED V | 2023-09-15 | R.ABBASSI | 2023-10-15 | 2023-10-19 | 2023-10-19 | On Time | F.OUZZA | 2023-10-26 | 2023-10-28 | 2023-10-27 | Late
11504 | E92911181000 | A00 | NZ0184296 | 2010VB | 008-A11-2 | XXXL |  | DB807 | DR-0000028043 | FINISHED V | 2023-09-15 | R.ABBASSI | 2023-10-15 | 2023-10-19 | 2023-10-19 | On Time | F.OUZZA | 2023-10-26 | 2023-10-28 | 2023-10-27 | Late
11504 | E92911181000 | A00 | PL0183421 | 2010VB | 008-A11-2 | XXXL |  | DB807 |  | FINISHED V | 2023-09-15 | R.ABBASSI | 2023-10-15 | 2023-10-19 | 2023-10-19 | On Time | F.OUZZA | 2023-10-26 | 2023-10-28 | 2023-10-27 | Late
11504 | E92911181000 | A00 | RDR0181352 | 2010VB | 008-A11-2 | XXXL |  | DB807 | DR-0000028039 | FINISHED V | 2023-09-15 | R.ABBASSI | 2023-10-15 | 2023-10-19 | 2023-10-19 | On Time | F.OUZZA | 2023-10-26 | 2023-10-28 | 2023-10-27 | Late
11504 | E92911181000 | A00 | RDR0181806 | 2010VB | 008-A11-2 | XXXL |  | DB807 | DR-0000028039 | FINISHED V | 2023-09-15 | R.ABBASSI | 2023-10-15 | 2023-10-19 | 2023-10-19 | On Time | F.OUZZA | 2023-10-26 | 2023-10-28 | 2023-10-27 | Late
11504 | E92911181000 | A00 | RDR0181425 | 2010VB | 008-A11-2 | XXXL |  | DB807 | DR-0000028039 | FINISHED V | 2023-09-15 | R.ABBASSI | 2023-10-15 | 2023-10-19 | 2023-10-19 | On Time | F.OUZZA | 2023-10-26 | 2023-10-28 | 2023-10-27 | Late
11504 | E92911181000 | A00 | NZ0184672 | 2010VB | 008-A11-2 | XXXL |  | DB807 | DR-0000028080 | FINISHED V | 2023-09-15 | R.ABBASSI | 2023-10-15 | 2023-10-19 | 2023-10-19 | On Time | F.OUZZA | 2023-10-26 | 2023-10-28 | 2023-10-27 | Late
11504 | E92911181000 | A00 | NZ0184892 | 2010VB | 008-A11-2 | XXXL |  | DB807 | DR-0000028135 | FINISHED V | 2023-10-26 | R.ABBASSI | 2023-10-15 | 2023-10-19 | 2023-10-19 | On Time | F.OUZZA | 2023-10-26 | 2023-10-28 | 2023-10-27 | Late
11504 | E92911181000 | A00 | NZ0184794 | 2010VB | 008-A11-2 | XXXL |  | DB807 | DR-0000028140 | FINISHED V | 2023-10-26 | R.ABBASSI | 2023-10-15 | 2023-10-19 | 2023-10-19 | On Time | F.OUZZA | 2023-10-26 | 2023-10-28 | 2023-10-27 | Late
11504 | E92911181000 | A00 | RDR0185138 | 2010VB | 008-A11-2 | XXXL |  | DB807 | DR-0000028195 | FINISHED V | 2023-11-10 | A.AZIL | 2023-11-10 | 2023-11-10 | 2023-11-10 | On Time | R.ABBASSI | 2023-11-10 | 2023-11-10 | 2023-11-10 | On Time
11504 | E92911181000 | A00 | EVO-23-134 | 2010VB | 008-A11-2 | XXXL |  | DB807 | EVO-23-134 | FINISHED V | 2023-11-13 | A.AZIL | 2023-11-13 | 2023-11-13 | 2023-11-13 | On Time | R.ABBASSI | 2023-11-13 | 2023-11-13 | 2023-11-13 | On Time
11504 | E92911181000 | A00 | EVO-23-149 | 2010VB | 008-A11-2 | XXXL |  | DB807 | EVO-23-149 | FINISHED V | 2023-11-23 | R.ABBASSI | 2023-11-23 | 2023-11-23 | 2023-11-23 | On Time | K.GHLIMI | 2023-11-23 | 2023-11-23 | 2023-11-23 | On Time
12126 | E92911181000 | A00 | Création 3DX | 2010VB | 006-A11 | XXXL |  | DB807 | DR-0000028061 | FINISHED V | 2023-11-14 | A.ELMOUSSAOUI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
12126 | E92911154000 | A00 | RDR0181729 | 2010VB | 006-A11 | XXXL |  | DB807 |  | FINISHED V
12126 | E92911154000 | A00 | RDR0181425 | 2010VB | 006-A11 | XXXL |  | DB807 | DR-0000028061; DQN Annulée | FINISHED V
12126 | E92911154000 | A00 | RDR0181352 | 2010VB | 006-A11 | XXXL |  | DB807 | DR-0000028061 | FINISHED V
12126 | E92911154000 | A00 | PL0183421 | 2010VB | 006-A11 | XXXL |  | DB807 |  | FINISHED V | 2023-11-14 | K.GHLIMI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
12126 | E92911154000 | A00 | RDR0182287 | 2010VB | 006-A11 | XXXL |  | DB807 |  | FINISHED V | 2023-11-14 | K.GHLIMI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
12126 | E92911154000 | A00 | NZ0184296 | 2010VB | 006-A11 | XXXL |  | DB807 | DR-0000028061 | FINISHED V | 2023-11-14 | K.GHLIMI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
12126 | E92911154000 | A00 | PL0183968 | 2010VB | 006-A11 | XXXL |  | DB807 | DR-0000028061 | FINISHED V | 2023-11-14 | K.GHLIMI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
12126 | E92911154000 | A00 | RDR0182877 | 2010VB | 006-A11 | XXXL |  | DB807 | DQN Annulée | FINISHED V | 2023-11-14 | K.GHLIMI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
12126 | E92911154000 | A00 | NZ0184672 | 2010VB | 006-A11 | XXXL |  | DB807 | DR-0000028081 | FINISHED V | 2023-11-14 | K.GHLIMI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
12126 | E92911154000 | A00 | NZ0184892 | 2010VB | 006-A11 | XXXL |  | DB807 | DR-0000028134 | FINISHED V | 2023-11-14 | K.GHLIMI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
12126 | E92911154000 | A00 | NZ0184794 | 2010VB | 006-A11 | XXXL |  | DB807 | DR-0000028139 | FINISHED V | 2023-11-14 | K.GHLIMI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
12126 | E92911154000 | A00 | RDR0185138 | 2010VB | 006-A11 | XXXL |  | DB807 | DR-0000028196 | FINISHED V | 2023-11-14 | K.GHLIMI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
12126 | E92911154000 | A00 | RDR0185178 | 2010VB | 006-A11 | XXXL |  | DB807 | DR-0000028214 | FINISHED V | 2023-11-14 | K.GHLIMI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
11504 | E92911181000 | EVO | APP EVO | 2010VB | 008-A11-3 | XXXL |  | DB807 | EVO 23-155 | FINISHED V | 2023-11-28 | A.AZIL | 2023-11-28 | 2023-11-28 | 2023-11-28 | On Time | R.ABBASSI | 2023-11-28 | 2023-11-28 | 2023-11-28 | On Time
12126 | E92911154000 | EVO | EVO 23-163 | 2010VB | 006-B10-1 | XXXL |  | DB807 | EVO 23-163 | FINISHED V |  | K.GHLIMI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
12126 | E92911154000 | PL | PL0185897 | 2010VB | 006-B11 | XXXL |  | DB807 |  | FINISHED V |  | K.GHLIMI | 2023-11-24 | 2023-11-24 |  |  | R.ABBASSI | 2023-11-24 | 2023-11-24
11590 | E92911089000 | D00 | Création 3DX | 2010VB | 002-D | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | RDR0181581 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | NZ0184892 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | NZ0184296 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | NZ0184672 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | RDR0182877 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | PL0183421 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | RDR0181352 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | RDR0182287 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | PL0181991 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | RDR0185138 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | NZ0184794 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | RDR0181806 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | RDR0181736 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | RDR0181445 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11590 | E92911089000 | D00 | RDR0181425 | 2010VB | 002-D15 | XXXL |  | DB807 |  | FINISHED V |  | R.ABBASSI | 2024-12-01 | 2024-12-01 |  |  | K.GHLIMI | 2023-12-01 | 2023-12-01
11520 | E92911105000 | A00 | PL0183968 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | NZ0184296 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | NZ0184892 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | NZ0184794 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | RDR0185138 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | NZ0184672 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | RDR0182877 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | RDR0181736 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | RDR0181581 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | RDR0182287 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | RDR0181445 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | RDR0181425 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | RDR0181806 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | RDR0181352 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | PL0183421 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028498 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 | PL0185897 | 2010VB | 005-A16 | XXXL |  | DB807 | DR-0000028412 | FINISHED V | 2024-01-19 | R.ABBASSI | 2024-01-24 | 2024-01-29 |  |  | F.OUZZA | 2024-01-30 | 2024-02-01
11520 | E92911105000 | A00 |  | 2010VB | 005-A17 | XXXL |  | DB807 |  | FINISHED V | 2024-02-26 | R.ABBASSI | 2024-02-26 | 2024-02-26 |  |  | F.OUZZA | 2024-02-26 | 2024-02-26
11520 | E92911105000 | A00 | PL0187188 | 2010VB | 005-A18 | XXXL |  | DB807 |  | FINISHED V | 2024-02-27 | R.ABBASSI | 2024-02-26 | 2024-02-26 |  |  | F.OUZZA | 2024-02-27 | 2024-02-27
11520 | E92911105000 | A00 | PL0187189 | 2010VB | 005-A19 | XXXL |  | DB807 |  | FINISHED V | 2024-02-27 | R.ABBASSI | 2024-02-26 | 2024-02-26 |  |  | F.OUZZA | 2024-02-27 | 2024-02-27
11520 | E92911105000 | A00 | PL0187211 | 2010VB | 005-A20 | XXXL |  | DB807 |  | FINISHED V | 2024-02-27 | R.ABBASSI | 2024-02-27 | 2024-02-27 |  |  | F.OUZZA | 2024-02-27 | 2024-02-27
11686 | E92911207000 | A00 | RDR0181581 | 2010VB | 009-A13 | XXXL |  | DB807 | DR-0000028530 | FINISHED V | 2024-01-26 | R.ABBASSI | 2024-02-02 | 2024-02-06 |  |  | F.OUZZA | 2024-02-26 | 2024-02-29
11686 | E92911207000 | A00 | PL0185897 | 2010VB | 009-A13 | XXXL |  | DB807 | DR-0000028530 | FINISHED V | 2024-01-26 | R.ABBASSI | 2024-02-02 | 2024-02-06 |  |  | F.OUZZA | 2024-02-26 | 2024-02-29
11686 | E92911207000 | A00 | RDR0185138 | 2010VB | 009-A13 | XXXL |  | DB807 | DR-0000028530 | FINISHED V | 2024-01-26 | R.ABBASSI | 2024-02-02 | 2024-02-06 |  |  | F.OUZZA | 2024-02-26 | 2024-02-29
11686 | E92911207000 | A00 | NZ0184892 | 2010VB | 009-A13 | XXXL |  | DB807 | DR-0000028530 | FINISHED V | 2024-01-26 | R.ABBASSI | 2024-02-02 | 2024-02-06 |  |  | F.OUZZA | 2024-02-26 | 2024-02-29
11686 | E92911207000 | A00 | NZ0184794 | 2010VB | 009-A13 | XXXL |  | DB807 | DR-0000028530 | FINISHED V | 2024-01-26 | R.ABBASSI | 2024-02-02 | 2024-02-06 |  |  | F.OUZZA | 2024-02-26 | 2024-02-29
11686 | E92911207000 | A00 | RDR0181352 | 2010VB | 009-A13 | XXXL |  | DB807 | DR-0000028530 | FINISHED V | 2024-01-26 | R.ABBASSI | 2024-02-02 | 2024-02-06 |  |  | F.OUZZA | 2024-02-26 | 2024-02-29
11686 | E92911207000 | A00 | RDR0181425 | 2010VB | 009-A13 | XXXL |  | DB807 | DR-0000028530 | FINISHED V | 2024-01-26 | R.ABBASSI | 2024-02-02 | 2024-02-06 |  |  | F.OUZZA | 2024-02-26 | 2024-02-29
11686 | E92911207000 | A00 | RDR0181445 | 2010VB | 009-A13 | XXXL |  | DB807 | DR-0000028530 | FINISHED V | 2024-01-26 | R.ABBASSI | 2024-02-02 | 2024-02-06 |  |  | F.OUZZA | 2024-02-26 | 2024-02-29
11686 | E92911207000 | A00 | NZ0184672 | 2010VB | 009-A13 | XXXL |  | DB807 | DR-0000028530 | FINISHED V | 2024-01-26 | R.ABBASSI | 2024-02-02 | 2024-02-06 |  |  | F.OUZZA | 2024-02-26 | 2024-02-29
11686 | E92911207000 | A00 | NZ0184296 | 2010VB | 009-A13 | XXXL |  | DB807 | DR-0000028530 | FINISHED V | 2024-01-26 | R.ABBASSI | 2024-02-02 | 2024-02-06 |  |  | F.OUZZA | 2024-02-26 | 2024-02-29
11686 | E92911207000 | A00 | PL0181991 | 2010VB | 009-A13 | XXXL |  | DB807 | DR-0000028530 | FINISHED V | 2024-01-26 | R.ABBASSI | 2024-02-02 | 2024-02-06 |  |  | F.OUZZA | 2024-02-26 | 2024-02-29
11686 | E92911207000 | A00 | RDR0181806 | 2010VB | 009-A13 | XXXL |  | DB807 | DR-0000028530 | FINISHED V | 2024-01-26 | R.ABBASSI | 2024-02-02 | 2024-02-06 |  |  | F.OUZZA | 2024-02-26 | 2024-02-29
12412 | E92911208000 | A00 | RDR0181352 | 2010VB | 010-A12 | XXXL |  | DB807 | DR-0000028548 | FINISHED V | 2024-01-31
12412 | E92911208000 | A00 | RDR0185138 | 2010VB | 010-A12 | XXXL |  | DB807 | DR-0000028548 | FINISHED V | 2024-01-31
12412 | E92911208000 | A00 | PL0185897 | 2010VB | 010-A12 | XXXL |  | DB807 | DR-0000028548 | FINISHED V | 2024-01-31
12412 | E92911208000 | A00 | NZ0184672 | 2010VB | 010-A12 | XXXL |  | DB807 | DR-0000028548 | FINISHED V | 2024-01-31
12412 | E92911208000 | A00 | NZ0184296 | 2010VB | 010-A12 | XXXL |  | DB807 | DR-0000028548 | FINISHED V | 2024-01-31
12412 | E92911208000 | A00 | PL0181991 | 2010VB | 010-A12 | XXXL |  | DB807 | DR-0000028548 | FINISHED V | 2024-01-31
12412 | E92911208000 | A00 | RDR0181806 | 2010VB | 010-A12 | XXXL |  | DB807 | DR-0000028548 | FINISHED V | 2024-01-31
12412 | E92911208000 | A00 | NZ0184892 | 2010VB | 010-A12 | XXXL |  | DB807 | DR-0000028548 | FINISHED V | 2024-01-31
12412 | E92911208000 | A00 | RDR0181581 | 2010VB | 010-A12 | XXXL |  | DB807 | DR-0000028548 | FINISHED V | 2024-01-31
12412 | E92911208000 | A00 | NZ0184794 | 2010VB | 010-A12 | XXXL |  | DB807 | DR-0000028548 | FINISHED V | 2024-01-31
12412 | E92911208000 | A00 | RDR0181445 | 2010VB | 010-A12 | XXXL |  | DB807 | DR-0000028548 | FINISHED V | 2024-01-31
12412 | E92911208000 | A00 | RDR0181425 | 2010VB | 010-A12 | XXXL |  | DB807 | DR-0000028548 | FINISHED V | 2024-01-31
11631 | E92911162000 | A00 | NZ0184672 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | PL0183421 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | PL0185897 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | RDR0185138 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | RDR0181581 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | RDR0181445 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | RDR0181425 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | RDR0181352 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | NZ0184892 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | NZ0184794 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | NZ0184296 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | RDR0181736 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | RDR0181806 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | RDR0182287 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | RDR0182877 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028510 | FINISHED V | 2024-01-23 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
11631 | E92911162000 | A00 | RDR0186454 | 2010VB | 004-A16 | XXXL |  | DB807 | DR-0000028544 | FINISHED V | 2024-01-31 | R.ABBASSI | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | F.OUZZA | 2024-02-26 | 2024-02-29 | 2024-02-29
12348 | E92911209000 | A00 | Création | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | RDR0181445 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | RDR0181425 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | RDR0181352 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | PL0185897 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | NZ0184794 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | NZ0184892 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | RDR0185138 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | NZ0184672 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | NZ0184296 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | PL0181991 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | RDR0181806 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | RDR0187095 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028622 | FINISHED V | 2024-02-19 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | PL0187188 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | PL0187189 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12348 | E92911209000 | A00 | PL0187211 | 2010VB | 011-A15 | XXXL |  | DB807 | DR-0000028759 | FINISHED V | 2024-03-27 | R.ABBASSI | 2024-04-08 | 2024-04-08 |  |  | M.BOULAAJOUL | 2024-04-08 | 2024-04-08
12370 | E92911185000 | A00 | Création | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | NZ0184296 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | NZ0184672 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | NZ0184794 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | NZ0184892 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | PL0185897 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | RDR0181352 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | RDR0181425 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | RDR0181445 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | RDR0185138 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | RDR0185178 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | PL0187188 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | PL0187189 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028686 | FINISHED V | 2024-02-29 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
12370 | E92911185000 | A00 | NZ0188008 | 2010VB | 007-A13 | XXXL |  | DB807 | DR-0000028898 | FINISHED V | 2024-04-26 | R.ABBASSI | 2024-04-19 | 2024-04-23 |  |  | M.BOULAAJOUL | 2024-04-23 | 2024-04-26
Formulas:
Progress Design = IF(AND([End Date]="",AND([Due Date Design]<>0,[Due Date Design]<TODAY())),"Late",IF([Status]="BLOCKED Data","BLOCKED",IF([Due Date Design]="","",IF([End Date]<=[Due Date Design],"On Time",IF([End Date]>[Due Date Design],"Late")))))
Progress Check = IF(AND([End Date]="",AND([Due Date Check]<>0,[Due Date Check]<TODAY())),"Late",IF([Due Date Design]="BLOCKED Data","BLOCKED",IF([Due Date Check]="","",IF([End Date]<=[Due Date Check],"On Time",IF([End Date]>[Due Date Check],"Late")))))